## Step 1
Time Tracking
Question | Details/Remarks | Report
By how many days will the project deadline be extended due to the current delay? | Working days | 5
By how much have costs increased due to delays? | Time related costs - 500$/day | -2500
What will the total deviation from the plan be in days if similar delays continue? | Expected total delay from baseline plan | 67
What will the total deviation from the budget be if similar delays continue? | Total Expected overspending due to delays | -33500
What can be done to prevent delays from recurring in the future? | brainstormed ideas for project crushing
1. Increase number of workers | Total cost of decision | -7000
2. Increase volume of equipment | Total cost of decision | -15000
3. Change concrete vendor | Total cost of decision | -22000
Budget Control
Question | Details/Remarks | Report
How much value is earned in real terms (not considering price inflations over baseline budget) | Budgeted cost of works scheduled (BCWS) | 300000
| Budgeted cost of work performed (BCWP) | 250000
| BCWP/BCWS | 83.33%
| Days are we behind the baseline plan? | 10
| Volume behind baseline plan | 50000
How much value we lost due to overspending? | Budgeted cost of work performed (BCWP) | 250000
| Actual cost of work performed (AC) | 266000
| Spending above baseline | -16000
| - Material price deviation | -6000
| - Material amount deviation | -1000
| - Workforce price deviation | -2000
| - Quality improvements | -7000
How will the project's total budget change based on the reasons for overspending? | Expected spending above baseline | -118000
| - Material price deviation | -32000
| - Material amount deviation | -12000
| - Workforce price deviation | -20000
| - Quality improvements | -54000
Should we? | Make changes in project composition? | [Yes/No, e.g., adjust architecture]
| Make changes in project execution? | [Yes/No, e.g. adjust subcontractor]
| Apply variance to consumer prices? | [Yes/No, increase price by 2%]
| Accept reduced profitability? | [Yes/No, state rationale]
Risk Assessment for Near Future
Question - Details/Remarks | Issues to pay attention | Actions Taken or Planned
What are the key logistics risks? On-time delivery of critical materials | [e.g. Windows & Drors delivery] | [Start tender process immediately]
What are the key quality risks? - Avoiding unnecessary improvements | [e.g. Straightness of the walls] | [Implement digital monitoring system]
What are the key work-in-time risks? - Ensuring effective progress | [e.g. accomplishment of daily plans of concrete block cladding] | [Ensure proper number of working stuff]